[ Insert official UPAEP logo ]

UPAEP · Decanato de Ingenierías

DAILY MEETING 1

Sprint 2 - Meeting Record

SmartGreenAI: Cilantro Crop

| Course | Agile Project Management |
| --- | --- |
| Project | SmartGreenAI: Cilantro Crop |
| Students | Jorge Velez Delgado Vicente Rocha Alfaro Oscar Abraham Talavera Nava Carlos Ramirez Mendoza Alexis Enrique Valle Parra |
| Professor | Jorge Rafael Aguilar Cisneros |
| Sprint | Sprint 2 (September 21, 2026 – October 9, 2026) |
| Date | September 21, 2026 |

# 1. Meeting Information

| Date | September 21, 2026 |
| --- | --- |
| Time | 4:30 PM |
| Meeting | Sprint 2 Planning + Daily Meeting 1 |
| Sprint week | Week 1 (Sep 21 – Sep 25) — start of the sprint |
| Facilitator | Jorge Velez Delgado (Scrum Master) |
| Sprint status | On track |

# 2. Attendees

- Jorge Velez Delgado

- Vicente Rocha Alfaro

- Oscar Abraham Talavera Nava

- Carlos Ramirez Mendoza

- Alexis Enrique Valle Parra

# 3. Topics Discussed

- The team reviewed the Sprint 1 results and agreed to carry over US-01 as US-01-C to finish secure role-based login.

- The Sprint 2 Goal, backlog and task breakdown were confirmed. All tasks were estimated in whole hours between 1 and 5 h (42 h in total).

- The team agreed to hold the Daily Scrum once a week, every Monday at 4:30 PM, because every member dedicates about 5 hours per week to the project.

- Physical sensors are still not available, so Vicente will build a simulator script that sends realistic cilantro values to the cloud.

# 4. Team Update

Each member answered: what did I finish (previous sprint), what will I do this week, and is anything blocking me?

| Team member | Finished (previous sprint) | Plan for this week | Blockers / help needed |
| --- | --- | --- | --- |
| Jorge Velez Delgado | Compiled the Sprint 1 retrospective actions and prepared the Sprint 2 board. | US10-T1 threshold data model and default cilantro values; US10-T2 threshold screen design. | None. |
| Vicente Rocha Alfaro | Finished the Sprint 1 user and role management designs (US-22, US-24). | US06-T1 data flow and payload format; US06-T2 cloud service configuration. | Needs the final sensor IDs. Resolved in the meeting: SM-01, SM-02 and TMP-01 from Sprint 1. |
| Oscar Abraham Talavera Nava | Finished the sensor simulation evidence of Sprint 1 (US-03, US-04, US-05). | US07-T1 ER diagram, US07-T2 database schema and US14-T1 actuator states. | None. |
| Carlos Ramirez Mendoza | Finished the dashboard prototype of Sprint 1 (US-09). | US08-T1 API specification (to share by Wednesday) and US08-T2 API project. | Needs the ER draft from Oscar. Agreed to pair on Tuesday. |
| Alexis Enrique Valle Parra | Finished the login design and credential test cases of Sprint 1 (US-01). | Close US-01-C this week (US01C-T1 to T4) and US25-T1 device registry model. | None. |

# 5. Scrum Board and Burndown Status

| Tasks in the sprint | 34 development tasks + 2 sprint-level tasks |
| --- | --- |
| Planned hours | 42 h |
| Done | 0 tasks (0 h) |
| Remaining | 42 h |
| Planned for this week | 14 tasks (16 h) |

# 6. Decisions and Action Items

- Cloud database: PostgreSQL (compatible with Supabase). Backend: Node.js + Express REST API with JWT sessions and device API keys.

- Measurement payload: sensor_id, value, unit and recorded_at in UTC (to be confirmed in US06-T1 and US08-T1).

- Weekly Daily Scrum every Monday at 4:30 PM; board and burndown updated by the Scrum Master after each meeting.

# 7. Meeting Conclusion

The team committed to the Sprint 2 Goal and the 42-hour backlog. Every member knows their Week 1 tasks and the dependencies on the API specification and the data model.