[ Insert official UPAEP logo ]

UPAEP · Decanato de Ingenierías

DAILY MEETING 3

Sprint 2 - Meeting Record

SmartGreenAI: Cilantro Crop

| Course | Agile Project Management |
| --- | --- |
| Project | SmartGreenAI: Cilantro Crop |
| Students | Jorge Velez Delgado Vicente Rocha Alfaro Oscar Abraham Talavera Nava Carlos Ramirez Mendoza Alexis Enrique Valle Parra |
| Professor | Jorge Rafael Aguilar Cisneros |
| Sprint | Sprint 2 (September 21, 2026 – October 9, 2026) |
| Date | October 5, 2026 |

# 1. Meeting Information

| Date | October 5, 2026 |
| --- | --- |
| Time | 4:30 PM |
| Meeting | Daily Meeting 3 |
| Sprint week | Start of Week 3 (Oct 5 – Oct 9) |
| Facilitator | Jorge Velez Delgado (Scrum Master) |
| Sprint status | On track |

# 2. Attendees

- Jorge Velez Delgado

- Vicente Rocha Alfaro

- Oscar Abraham Talavera Nava

- Carlos Ramirez Mendoza

- Alexis Enrique Valle Parra

# 3. Topics Discussed

- Review of the Week 2 milestone: all endpoints, storage, transmission, threshold, registry and actuator features implemented and connected.

- The integration check of Friday worked: simulator → POST /measurements → database → GET /sensors/{id}/measurements.

- US06-T3 took 3 h instead of 2 h and US08-T4 took 2 h instead of 1 h; the Week 3 buffer absorbs the difference.

- Week 3 plan: tests, evidence, end-to-end integration test (SPR-T1) on Thursday October 8, Sprint Review and Retrospective on Friday October 9.

# 4. Team Update

Each member answered: what did I finish last week, what will I do this week, and is anything blocking me?

| Team member | Finished last week | Plan for this week | Blockers / help needed |
| --- | --- | --- | --- |
| Jorge Velez Delgado | US10-T3 and US10-T4 finished; thresholds saved with user and date. | US10-T5 threshold tests; facilitate SPR-T1 and prepare the Review with Alexis (SPR-T2). | None. |
| Vicente Rocha Alfaro | US06-T3 sending from simulator every 60 s; US06-T4 retry and buffer tested with the network cut. | US06-T5 end-to-end transmission test with at least 100 readings. | None. |
| Oscar Abraham Talavera Nava | US07-T3, US07-T4, US14-T2 and US14-T3 finished; panel refreshes every 30 s. | US07-T5 storage tests and US14-T4 actuator status tests. | The OFFLINE state needs a recent update from the device; agreed with Vicente that the device sends a heartbeat. |
| Carlos Ramirez Mendoza | US08-T3, US08-T4 and US08-T5 finished; every error follows the documented format. | US08-T6 Postman collection and full run. | None. |
| Alexis Enrique Valle Parra | US25-T1 to US25-T4 finished; new devices receive an API key and deactivated keys are rejected. | US25-T5 registration flow test; SPR-T2 evidence compilation with Jorge. | None. |

# 5. Scrum Board and Burndown Status

| Done | 28 tasks (34 h) |
| --- | --- |
| Remaining | 8 h (ideal line: 14 h) |
| Planned for this week | 6 tasks (8 h) + 2 sprint-level tasks |
| Tasks moved to Done last week | US06-T3, US06-T4, US07-T3, US07-T4, US08-T3, US08-T4, US08-T5, US10-T3, US10-T4, US14-T2, US14-T3, US25-T2, US25-T3, US25-T4 |

# 6. Decisions and Action Items

- Feature freeze: no new features during Week 3.

- Every member uploads the evidence of each task with the name <TaskID>_<Task_Name> to the Sprint 2 evidence folder before Thursday.

# 7. Meeting Conclusion

All implementation tasks are done. The team enters the testing week with 8 hours of planned work and a buffer for defect fixing.