[ Insert official UPAEP logo ]

UNIVERSIDAD POPULAR AUTÓNOMA

DEL ESTADO DE PUEBLA

Decanato de Ingenierías

Course: Agile Project Management

SPRINT 2

SPRINT REVIEW & DELIVERY

SmartGreenAI: Cilantro Crop

Sprint Backlog, Execution Evidence and Increment (September 21, 2026 – October 9, 2026)

Professor

Jorge Rafael Aguilar Cisneros

Team members

| Student | Student ID | Scrum role |
| --- | --- | --- |
| Jorge Velez Delgado | [ID] | Scrum Master / Developer |
| Vicente Rocha Alfaro | [ID] | Developer |
| Oscar Abraham Talavera Nava | [ID] | Developer |
| Carlos Ramirez Mendoza | [ID] | Developer |
| Alexis Enrique Valle Parra | [ID] | Product Owner / Developer |

Puebla, Puebla — September 2026

# 1. Sprint Summary

| Sprint | Sprint 2 — IoT Cloud Communication, Storage and APIs |
| --- | --- |
| Dates | September 21, 2026 – October 9, 2026 (3 weeks) |
| Sprint Goal | Extend the SmartGreenAI platform by enabling cloud communication and data storage for IoT measurements, providing APIs for system integration, configuring environmental thresholds, displaying actuator status, managing IoT infrastructure, and completing secure role-based login. |
| Result | Sprint Goal achieved. All committed user stories are Done and accepted by the Product Owner. |
| User stories | 7 committed / 7 done |
| Tasks | 34 development tasks + 2 sprint-level tasks, all Done |
| Hours | 42 h planned / 44 h actual (velocity: 42 h of committed work completed) |
| Review date | October 9, 2026, 4:30 PM |

# 2. Sprint Goal Assessment

Measurable goal: a registered sensor sends measurements to the cloud, they are stored with sensor ID and timestamp, they can be consulted through the API, an administrator can configure thresholds, and a logged-in producer can see the status of every actuator.

Assessment: the measurable goal was demonstrated live at the Sprint Review (section 8). Transmission test result: 100 readings sent, 99 stored correctly (99%), average delay 1.4 s.

# 3. Sprint Backlog — Final Status

| ID | User Story | Priority | Owner | Plan h | Actual h | Status |
| --- | --- | --- | --- | --- | --- | --- |
| US-01-C | Complete secure login and role-based access | Must | Alexis Enrique Valle Parra | 4 | 4 | Done |
| US-06 | Transmit IoT measurements to the cloud | Must | Vicente Rocha Alfaro | 8 | 9 | Done |
| US-07 | Store measurements with sensor IDs and timestamps | Must | Oscar Abraham Talavera Nava | 5 | 5 | Done |
| US-08 | Provide APIs for IoT devices and web application | Must | Carlos Ramirez Mendoza | 8 | 9 | Done |
| US-10 | Configure sensor thresholds | Must | Jorge Velez Delgado | 5 | 5 | Done |
| US-14 | View actuator status | Must | Oscar Abraham Talavera Nava | 4 | 4 | Done |
| US-25 | Register IoT devices, sensors and actuators | Could | Alexis Enrique Valle Parra | 8 | 8 | Done |
|  | Total Sprint 2 |  |  | 42 | 44 |  |

Estimation variance: US06-T3 took 3 h instead of 2 h; US08-T4 took 2 h instead of 1 h. The Week 3 buffer absorbed the difference.

# 4. Tasks Completed and Evidence

Every task has its evidence file in the folder Sprint 2/Evidence/<User Story>/. The file name starts with the task ID so that each completion condition can be traced to its proof.

## US-01-C — Complete secure login and role-based access

| Task ID | Task | Responsible | Hrs | Status | Evidence file |
| --- | --- | --- | --- | --- | --- |
| US01C-T1 | Connect the login form to the authentication service | Alexis Enrique Valle Parra | 1 | Done | US01C-T1_Connect_Login_Form_Authentication_Service.docx |
| US01C-T2 | Implement role-based access (RBAC) and redirection | Alexis Enrique Valle Parra | 1 | Done | US01C-T2_Implement_Role-Based_Access_RBAC_Redirection.docx |
| US01C-T3 | Build and run the permission matrix test | Alexis Enrique Valle Parra | 1 | Done | US01C-T3_Build_Run_Permission_Matrix_Test.docx |
| US01C-T4 | Test invalid credentials and unauthorized access | Alexis Enrique Valle Parra | 1 | Done | US01C-T4_Test_Invalid_Credentials_Unauthorized_Access.docx |

## US-06 — Transmit IoT measurements to the cloud

| Task ID | Task | Responsible | Hrs | Status | Evidence file |
| --- | --- | --- | --- | --- | --- |
| US06-T1 | Design the IoT-to-cloud data flow and message format | Vicente Rocha Alfaro | 2 | Done | US06-T1_Design_IoT-To-Cloud_Data_Flow_Message.docx |
| US06-T2 | Configure the cloud service and device authentication | Vicente Rocha Alfaro | 1 | Done | US06-T2_Configure_Cloud_Service_Device_Authentication.docx |
| US06-T3 | Implement measurement sending from the device (or simulator) | Vicente Rocha Alfaro | 3 | Done | US06-T3_Implement_Measurement_Sending_Device_Simulator.docx |
| US06-T4 | Handle connection failures | Vicente Rocha Alfaro | 1 | Done | US06-T4_Handle_Connection_Failures.docx |
| US06-T5 | End-to-end transmission test | Vicente Rocha Alfaro | 2 | Done | US06-T5_End-To-End_Transmission_Test.docx |

## US-07 — Store measurements with sensor IDs and timestamps

| Task ID | Task | Responsible | Hrs | Status | Evidence file |
| --- | --- | --- | --- | --- | --- |
| US07-T1 | Design the measurement data model | Oscar Abraham Talavera Nava | 1 | Done | US07-T1_Design_Measurement_Data_Model.docx |
| US07-T2 | Create the database schema | Oscar Abraham Talavera Nava | 1 | Done | US07-T2_Create_Database_Schema.docx |
| US07-T3 | Implement the storage service | Oscar Abraham Talavera Nava | 1 | Done | US07-T3_Implement_Storage_Service.docx |
| US07-T4 | Implement history queries | Oscar Abraham Talavera Nava | 1 | Done | US07-T4_Implement_History_Queries.docx |
| US07-T5 | Test storage and retrieval | Oscar Abraham Talavera Nava | 1 | Done | US07-T5_Test_Storage_Retrieval.docx |

## US-08 — Provide APIs for IoT devices and web application

| Task ID | Task | Responsible | Hrs | Status | Evidence file |
| --- | --- | --- | --- | --- | --- |
| US08-T1 | Write the API specification | Carlos Ramirez Mendoza | 2 | Done | US08-T1_API_Specification_SmartGreenAI.docx |
| US08-T2 | Set up the API project and security layer | Carlos Ramirez Mendoza | 1 | Done | US08-T2_Set_Up_API_Project_Security.docx |
| US08-T3 | Implement measurement endpoints | Carlos Ramirez Mendoza | 2 | Done | US08-T3_Implement_Measurement_Endpoints.docx |
| US08-T4 | Implement web application endpoints | Carlos Ramirez Mendoza | 2 | Done | US08-T4_Implement_Web_Application_Endpoints.docx |
| US08-T5 | Standardize validation and error responses | Carlos Ramirez Mendoza | 1 | Done | US08-T5_Standardize_Validation_Error_Responses.docx |
| US08-T6 | API test collection | Carlos Ramirez Mendoza | 1 | Done | US08-T6_API_Test_Collection.docx |

## US-10 — Configure sensor thresholds

| Task ID | Task | Responsible | Hrs | Status | Evidence file |
| --- | --- | --- | --- | --- | --- |
| US10-T1 | Define the threshold data model and default values | Jorge Velez Delgado | 1 | Done | US10-T1_Define_Threshold_Data_Model_Default.docx |
| US10-T2 | Design the threshold configuration screen | Jorge Velez Delgado | 1 | Done | US10-T2_Design_Threshold_Configuration_Screen.docx |
| US10-T3 | Implement create/update logic with validation | Jorge Velez Delgado | 1 | Done | US10-T3_Implement_Create_Update_Logic_Validation.docx |
| US10-T4 | Connect the screen to the API | Jorge Velez Delgado | 1 | Done | US10-T4_Connect_Screen_API.docx |
| US10-T5 | Test threshold configuration | Jorge Velez Delgado | 1 | Done | US10-T5_Test_Threshold_Configuration.docx |

## US-14 — View actuator status

| Task ID | Task | Responsible | Hrs | Status | Evidence file |
| --- | --- | --- | --- | --- | --- |
| US14-T1 | Define actuator states and data | Oscar Abraham Talavera Nava | 1 | Done | US14-T1_Define_Actuator_States_Data.docx |
| US14-T2 | Implement the current-status query | Oscar Abraham Talavera Nava | 1 | Done | US14-T2_Implement_Current-Status_Query.docx |
| US14-T3 | Build the actuator status panel | Oscar Abraham Talavera Nava | 1 | Done | US14-T3_Build_Actuator_Status_Panel.docx |
| US14-T4 | Test actuator status visualization | Oscar Abraham Talavera Nava | 1 | Done | US14-T4_Test_Actuator_Status_Visualization.docx |

## US-25 — Register IoT devices, sensors and actuators

| Task ID | Task | Responsible | Hrs | Status | Evidence file |
| --- | --- | --- | --- | --- | --- |
| US25-T1 | Define the device registry model | Alexis Enrique Valle Parra | 1 | Done | US25-T1_Define_Device_Registry_Model.docx |
| US25-T2 | Design the registration screens | Alexis Enrique Valle Parra | 1 | Done | US25-T2_Design_Registration_Screens.docx |
| US25-T3 | Implement register, edit and deactivate | Alexis Enrique Valle Parra | 3 | Done | US25-T3_Implement_Register_Edit_Deactivate.docx |
| US25-T4 | Generate device credentials | Alexis Enrique Valle Parra | 1 | Done | US25-T4_Generate_Device_Credentials.docx |
| US25-T5 | Test the registration flow | Alexis Enrique Valle Parra | 2 | Done | US25-T5_Test_Registration_Flow.docx |

## Sprint-level tasks

| Task ID | Task | Responsible | Status | Evidence file |
| --- | --- | --- | --- | --- |
| SPR-T1 | End-to-end integration test | Whole team (facilitated by Jorge) | Done | Sprint2_SPR-T1_End-To-End_Integration_Test.docx |
| SPR-T2 | Sprint Review preparation and evidence compilation | Jorge Velez Delgado + Alexis Enrique Valle Parra | Done | Sprint2_SPR-T2_Sprint_Review_Preparation_Evidence_Compilation.docx |

# 5. Acceptance Criteria Verification

| Story | Acceptance criterion | Result | Main evidence |
| --- | --- | --- | --- |
| US-01-C | Valid users log in and are redirected according to their role (Super Administrator, Administrator or Producer). | Met ✓ | US01C-T4_Test_Invalid_Credentials_Unauthorized_Access.docx |
|  | Passwords are never stored in plain text and sessions expire. | Met ✓ | US01C-T4_Test_Invalid_Credentials_Unauthorized_Access.docx |
|  | Invalid credentials, expired sessions and direct access to restricted URLs are rejected. | Met ✓ | US01C-T4_Test_Invalid_Credentials_Unauthorized_Access.docx |
| US-06 | Measurements are transmitted automatically from the sensor system (or simulator) to the cloud at the defined interval. | Met ✓ | US06-T5_End-To-End_Transmission_Test.docx |
|  | Each message contains device ID, sensor ID, value, unit and UTC timestamp. | Met ✓ | US06-T5_End-To-End_Transmission_Test.docx |
|  | At least 95% of the messages in the test run are received correctly. | Met ✓ | US06-T5_End-To-End_Transmission_Test.docx |
| US-07 | Every measurement is stored with sensor ID, value, unit and UTC timestamp. | Met ✓ | US07-T5_Test_Storage_Retrieval.docx |
|  | Measurements from unknown or inactive sensors are rejected. | Met ✓ | US07-T5_Test_Storage_Retrieval.docx |
|  | Measurements can be retrieved by sensor and by date/time range. | Met ✓ | US07-T5_Test_Storage_Retrieval.docx |
| US-08 | IoT devices and the web application exchange data only through the documented endpoints. | Met ✓ | US08-T6_API_Test_Collection.docx |
|  | Every endpoint requires authentication and respects user roles. | Met ✓ | US08-T6_API_Test_Collection.docx |
|  | Invalid requests return clear errors with the correct HTTP code. | Met ✓ | US08-T6_API_Test_Collection.docx |
| US-10 | An administrator can create and update min/max values for each environmental variable. | Met ✓ | US10-T5_Test_Threshold_Configuration.docx |
|  | Invalid values are rejected with a clear message. | Met ✓ | US10-T5_Test_Threshold_Configuration.docx |
|  | Producers can view but cannot modify thresholds. | Met ✓ | US10-T5_Test_Threshold_Configuration.docx |
| US-14 | The current status of each registered actuator is visible to authorized users. | Met ✓ | US14-T4_Test_Actuator_Status_Visualization.docx |
|  | The panel shows the time of the last update and refreshes automatically. | Met ✓ | US14-T4_Test_Actuator_Status_Visualization.docx |
|  | Actuators without recent updates are displayed as OFFLINE. | Met ✓ | US14-T4_Test_Actuator_Status_Visualization.docx |
| US-25 | An administrator can register, edit and deactivate devices, sensors and actuators. | Met ✓ | US25-T5_Test_Registration_Flow.docx |
|  | Every sensor and actuator has a unique ID linked to its device. | Met ✓ | US25-T5_Test_Registration_Flow.docx |
|  | Only registered and active devices can send measurements. | Met ✓ | US25-T5_Test_Registration_Flow.docx |

# 6. Burndown

Remaining planned hours at each Monday checkpoint compared with the ideal line.

| Checkpoint | Date | Ideal remaining h | Actual remaining h |
| --- | --- | --- | --- |
| Sprint start | September 21, 2026 | 42 | 42 |
| End of Week 1 | September 28, 2026 | 28 | 27 |
| End of Week 2 | October 5, 2026 | 14 | 8 |
| End of Week 3 | October 9, 2026 | 0 | 0 |

# 7. Definition of Done Check

| Story | Code in repo | Acceptance met | Tests + evidence | Conditions checked | Board updated | Peer review |
| --- | --- | --- | --- | --- | --- | --- |
| US-01-C | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| US-06 | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| US-07 | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| US-08 | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| US-10 | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| US-14 | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| US-25 | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |

# 8. Sprint Review Meeting

| Date | October 9, 2026, 4:30 PM |
| --- | --- |
| Attendees | Jorge Velez Delgado Vicente Rocha Alfaro Oscar Abraham Talavera Nava Carlos Ramirez Mendoza Alexis Enrique Valle Parra Professor Jorge Rafael Aguilar Cisneros (stakeholder) |
| Facilitator | Jorge Velez Delgado (Scrum Master) |
| Presenter of the increment | Every owner presented their own user story |

## Demonstration script

1. Login as Administrator and as Producer; each role lands on its own page and restricted routes return 403.

2. Register a new IoT device with its sensors and actuators and obtain its API key.

3. Start the simulator with that API key; measurements arrive every 60 s.

4. Show the measurements stored with sensor ID, value, unit, recorded_at and received_at.

5. Query the history of SM-01 through GET /sensors/SM-01/measurements with from/to filters in Postman.

6. Change the soil-moisture threshold as Administrator; show that the Producer can view but not edit it.

7. Show the actuator status panel refreshing and an actuator without heartbeat displayed as OFFLINE.

8. Cut the network of the simulator and show that buffered readings are delivered after reconnection.

## Feedback received

- Product Owner accepted the seven user stories: all acceptance criteria met.

- Stakeholder suggestion: show the measurement history as a chart, not only as a table (added to US-27 in Sprint 4).

- Stakeholder suggestion: keep the simulator as part of the final demo because the physical sensors may not be available.

## Product Backlog changes

- Historical graphs added as a task of US-27 (Sprint 4).

- US-17 (actuator events) proposed to move from Sprint 4 to Sprint 3 because irrigation will need it.

# 9. Increment Delivered

- Secure login integrated with user roles and its permission test matrix.

- IoT-to-cloud data flow diagram, working transmission and simulator script.

- Database model and measurement storage with sensor IDs and timestamps.

- API specification, implementation and Postman test collection.

- Environmental threshold configuration screen and logic.

- Actuator status panel in the dashboard.

- IoT device, sensor and actuator registration.

- End-to-end integration evidence and testing evidence for each Sprint 2 user story.

# 10. Evidence Folder Structure

Sprint 2/

Sprint_2_Planning_SmartGreenAI_Cilantro.docx

Daily_Meeting_1/2/3_Sprint_2_SmartGreenAI.docx

Sprint_2_Review_Delivery_SmartGreenAI_Cilantro.docx

Retrospective_Meeting_Sprint_2_SmartGreenAI.docx

Evidence/

US-01-C/  (US01C-T1, US01C-T2, US01C-T3, US01C-T4)

US-06/  (US06-T1, US06-T2, US06-T3, US06-T4, US06-T5)

US-07/  (US07-T1, US07-T2, US07-T3, US07-T4, US07-T5)

US-08/  (US08-T1, US08-T2, US08-T3, US08-T4, US08-T5, US08-T6)

US-10/  (US10-T1, US10-T2, US10-T3, US10-T4, US10-T5)

US-14/  (US14-T1, US14-T2, US14-T3, US14-T4)

US-25/  (US25-T1, US25-T2, US25-T3, US25-T4, US25-T5)

Sprint/  (SPR-T1, SPR-T2)

Each evidence document contains the task information, every completion condition marked with its proof (screenshot, log, query result, test table or diagram) and the list of attached files named <TaskID>_<Task_Name>_<n>.<ext>.

# 11. Next Sprint

Sprint 3 (October 12 – October 30, 2026) will add threshold alerts with severity and history, manual and automatic irrigation, the actuator event log (pulled forward from Sprint 4) and anomaly detection. No stories are carried over.

# 12. Scrum Roles

| Student | Role |
| --- | --- |
| Jorge Velez Delgado | Scrum Master / Developer |
| Vicente Rocha Alfaro | Developer |
| Oscar Abraham Talavera Nava | Developer |
| Carlos Ramirez Mendoza | Developer |
| Alexis Enrique Valle Parra | Product Owner / Developer |