[ Insert official UPAEP logo ]

UPAEP · Decanato de Ingenierías

DAILY MEETING 1

Sprint 3 - Meeting Record

SmartGreenAI: Cilantro Crop

| Course | Agile Project Management |
| --- | --- |
| Project | SmartGreenAI: Cilantro Crop |
| Students | Jorge Velez Delgado Vicente Rocha Alfaro Oscar Abraham Talavera Nava Carlos Ramirez Mendoza Alexis Enrique Valle Parra |
| Professor | Jorge Rafael Aguilar Cisneros |
| Sprint | Sprint 3 (October 12, 2026 – October 30, 2026) |
| Date | October 12, 2026 |

# 1. Meeting Information

| Date | October 12, 2026 |
| --- | --- |
| Time | 4:30 PM |
| Meeting | Sprint 3 Planning + Daily Meeting 1 |
| Sprint week | Week 1 (Oct 12 – Oct 16) — start of the sprint |
| Facilitator | Jorge Velez Delgado (Scrum Master) |
| Sprint status | On track |

# 2. Attendees

- Jorge Velez Delgado

- Vicente Rocha Alfaro

- Oscar Abraham Talavera Nava

- Carlos Ramirez Mendoza

- Alexis Enrique Valle Parra

# 3. Topics Discussed

- The team reviewed the Sprint 2 increment and the retrospective actions (evidence at Done, 48 h peer review, buffer for IoT tasks).

- The Sprint 3 Goal and backlog were confirmed: US-11, US-12, US-13, US-15, US-16, US-19 and US-17, pulled forward from Sprint 4. Total 43 h.

- The PO confirmed that the severity levels are Low, Medium and High ("Slow" in FR-14 is a typo for Low).

- Dependencies: the alert model, the command flow and the event log must be shared by Wednesday because US-16 depends on them.

# 4. Team Update

Each member answered: what did I finish (previous sprint), what will I do this week, and is anything blocking me?

| Team member | Finished (previous sprint) | Plan for this week | Blockers / help needed |
| --- | --- | --- | --- |
| Jorge Velez Delgado | Closed the Sprint 2 Review and updated the Product Backlog. | US11-T1 alert engine and alert data model. | None. |
| Vicente Rocha Alfaro | Delivered US-06 with 99% success rate in the transmission test. | US15-T1 command flow diagram; US15-T2 command endpoint. | None. |
| Oscar Abraham Talavera Nava | Delivered US-07 and US-14. | US16-T1 automatic irrigation rules; US16-T2 irrigation parameters screen. | Depends on the command flow of Vicente (Wednesday). |
| Carlos Ramirez Mendoza | Delivered US-08 and the Postman collection. | US12-T1 severity rules, US13-T1 alert history endpoint and US17-T1 event log. | None. |
| Alexis Enrique Valle Parra | Accepted the Sprint 2 stories as PO; delivered US-01-C and US-25. | US19-T1 anomaly detection methods. | The statistical method needs history data. |

# 5. Scrum Board and Burndown Status

| Tasks in the sprint | 28 development tasks + 2 sprint-level tasks |
| --- | --- |
| Planned hours | 43 h |
| Done | 0 tasks (0 h) |
| Remaining | 43 h |
| Planned for this week | 9 tasks (13 h) |

# 6. Decisions and Action Items

- US-17 is part of Sprint 3.

- Severity: Low ≤ 10%, Medium 10–25%, High > 25% of deviation (to be validated in US12-T1).

- The device will poll pending commands every 5 s (no inbound connection to the greenhouse).

# 7. Meeting Conclusion

The team committed to the Sprint 3 Goal and the 43-hour backlog.