[ Insert official UPAEP logo ]

UPAEP · Decanato de Ingenierías

DAILY MEETING 2

Sprint 3 - Meeting Record

SmartGreenAI: Cilantro Crop

| Course | Agile Project Management |
| --- | --- |
| Project | SmartGreenAI: Cilantro Crop |
| Students | Jorge Velez Delgado Vicente Rocha Alfaro Oscar Abraham Talavera Nava Carlos Ramirez Mendoza Alexis Enrique Valle Parra |
| Professor | Jorge Rafael Aguilar Cisneros |
| Sprint | Sprint 3 (October 12, 2026 – October 30, 2026) |
| Date | October 19, 2026 |

# 1. Meeting Information

| Date | October 19, 2026 |
| --- | --- |
| Time | 4:30 PM |
| Meeting | Daily Meeting 2 |
| Sprint week | Start of Week 2 (Oct 19 – Oct 23) |
| Facilitator | Jorge Velez Delgado (Scrum Master) |
| Sprint status | On track |

# 2. Attendees

- Jorge Velez Delgado

- Vicente Rocha Alfaro

- Oscar Abraham Talavera Nava

- Carlos Ramirez Mendoza

- Alexis Enrique Valle Parra

# 3. Topics Discussed

- Week 1 milestone reached: alert model, severity rules, command flow, irrigation rules and anomaly methods approved.

- Command endpoint, event log, alert history endpoint and irrigation parameters screen are available.

- The anomaly z-score method needs at least 24 h of history.

# 4. Team Update

Each member answered: what did I finish last week, what will I do this week, and is anything blocking me?

| Team member | Finished last week | Plan for this week | Blockers / help needed |
| --- | --- | --- | --- |
| Jorge Velez Delgado | US11-T1 finished and reviewed by Carlos. | US11-T2 alert evaluation on ingestion; US11-T3 alerts panel. | None. |
| Vicente Rocha Alfaro | US15-T1 sequence diagram approved; US15-T2 command endpoint with validation and 401/403. | US15-T3 command execution on device/simulator; US15-T4 control buttons and mode selector. | None. |
| Oscar Abraham Talavera Nava | US16-T1 rules approved by the PO (target 65%, max 10 min, cooldown 30 min); US16-T2 parameters screen. | US16-T3 automatic engine; US16-T4 safety conditions. | None; the command endpoint was ready on Friday. |
| Carlos Ramirez Mendoza | US12-T1, US13-T1 and US17-T1 finished; recordEvent shared with Vicente and Oscar. | US12-T2 severity display, US13-T2 history screen and US17-T2 irrigation history. | None. |
| Alexis Enrique Valle Parra | US19-T1 anomaly methods documented with examples. | US19-T2 anomaly service; US19-T3 anomaly display. | Needs history data (see decisions). |

# 5. Scrum Board and Burndown Status

| Done | 9 tasks (13 h) |
| --- | --- |
| Remaining | 30 h (ideal line: 29 h) |
| Planned for this week | 11 tasks (19 h) |
| Tasks moved to Done last week | US11-T1, US12-T1, US13-T1, US15-T1, US15-T2, US16-T1, US16-T2, US17-T1, US19-T1 |

# 6. Decisions and Action Items

- The seed script will generate 7 days of realistic historical data for all sensors; everyone uses the same seed (Sprint 2 retro action).

- Integration check by chat on Wednesday October 21 between alert engine, command flow and automatic engine.

# 7. Meeting Conclusion

Week 1 completed at 100%. Evidence of every finished task is already in the Sprint 3 folder.