[ Insert official UPAEP logo ]

UPAEP · Decanato de Ingenierías

DAILY MEETING 3

Sprint 3 - Meeting Record

SmartGreenAI: Cilantro Crop

| Course | Agile Project Management |
| --- | --- |
| Project | SmartGreenAI: Cilantro Crop |
| Students | Jorge Velez Delgado Vicente Rocha Alfaro Oscar Abraham Talavera Nava Carlos Ramirez Mendoza Alexis Enrique Valle Parra |
| Professor | Jorge Rafael Aguilar Cisneros |
| Sprint | Sprint 3 (October 12, 2026 – October 30, 2026) |
| Date | October 26, 2026 |

# 1. Meeting Information

| Date | October 26, 2026 |
| --- | --- |
| Time | 4:30 PM |
| Meeting | Daily Meeting 3 |
| Sprint week | Start of Week 3 (Oct 26 – Oct 30) |
| Facilitator | Jorge Velez Delgado (Scrum Master) |
| Sprint status | On track |

# 2. Attendees

- Jorge Velez Delgado

- Vicente Rocha Alfaro

- Oscar Abraham Talavera Nava

- Carlos Ramirez Mendoza — absent (sent update by the team chat)

- Alexis Enrique Valle Parra

# 3. Topics Discussed

- Week 2 milestone reached: alert engine, severity, command execution, irrigation control, automatic engine with safety rules and anomaly service implemented.

- US16-T3 took 4 h instead of 3 h because of a conflict between manual and automatic commands; US15-T3 took 3 h instead of 2 h.

- Carlos could not attend and sent his update by the team chat.

- Week 3 plan: feature freeze, tests, closed-loop simulation, SPR-T1 on Thursday October 29, Review and Retrospective on Friday October 30.

# 4. Team Update

Each member answered: what did I finish last week, what will I do this week, and is anything blocking me?

| Team member | Finished last week | Plan for this week | Blockers / help needed |
| --- | --- | --- | --- |
| Jorge Velez Delgado | US11-T2 and US11-T3 finished; alerts appear within 30 s. | US11-T4 alert tests; facilitate SPR-T1 and prepare the Review (SPR-T2). | None. |
| Vicente Rocha Alfaro | US15-T3 and US15-T4 finished; pump state changes in about 6 s. | US15-T5 manual irrigation tests. | None. |
| Oscar Abraham Talavera Nava | US16-T3 and US16-T4 finished; engine blocked by cooldown, low tank and stale data. | US16-T5 closed-loop simulation; US16-T6 automatic irrigation tests. | Resolved: manual/automatic conflict (see decisions). |
| Carlos Ramirez Mendoza | (By chat) US12-T2, US13-T2 and US17-T2 finished. | (By chat) US12-T3, US13-T3 and US17-T3 tests. | (By chat) None. |
| Alexis Enrique Valle Parra | US19-T2 and US19-T3 finished; five anomaly types stored and shown. | US19-T4 anomaly tests and false-positive measurement; SPR-T2 with Jorge. | None. |

# 5. Scrum Board and Burndown Status

| Done | 20 tasks (32 h) |
| --- | --- |
| Remaining | 11 h (ideal line: 14 h) |
| Planned for this week | 8 tasks (11 h) + 2 sprint-level tasks |
| Tasks moved to Done last week | US11-T2, US11-T3, US12-T2, US13-T2, US15-T3, US15-T4, US16-T3, US16-T4, US17-T2, US19-T2, US19-T3 |

# 6. Decisions and Action Items

- MANUAL mode disables the automatic engine for that area, and the engine never creates a command while another command is pending.

- Feature freeze from today.

# 7. Meeting Conclusion

All implementation tasks are done; 11 hours of testing and evidence remain for Week 3.