[ Insert official UPAEP logo ]

UPAEP · Decanato de Ingenierías

DAILY MEETING 3

Sprint 4 - Meeting Record

SmartGreenAI: Cilantro Crop

| Course | Agile Project Management |
| --- | --- |
| Project | SmartGreenAI: Cilantro Crop |
| Students | Jorge Velez Delgado Vicente Rocha Alfaro Oscar Abraham Talavera Nava Carlos Ramirez Mendoza Alexis Enrique Valle Parra |
| Professor | Jorge Rafael Aguilar Cisneros |
| Sprint | Sprint 4 (November 2, 2026 – November 20, 2026) |
| Date | November 16, 2026 |

# 1. Meeting Information

| Date | November 16, 2026 |
| --- | --- |
| Time | 4:30 PM |
| Meeting | Daily Meeting 3 |
| Sprint week | Start of Week 3 (Nov 16 – Nov 20) |
| Facilitator | Jorge Velez Delgado (Scrum Master) |
| Sprint status | On track |

# 2. Attendees

- Jorge Velez Delgado

- Vicente Rocha Alfaro

- Oscar Abraham Talavera Nava

- Carlos Ramirez Mendoza

- Alexis Enrique Valle Parra

# 3. Topics Discussed

- Week 2 milestone reached: trend identification, recommendation engine, explanations and integrated dashboard implemented.

- US20-T3 took 5 h instead of 4 h and US27-T3 took 4 h instead of 3 h.

- Functional tests: 28 of 30 FR passed. Defects: FR-11 disconnection shown after 10 min instead of 5 min; FR-21 threshold changes not stored as user activity. Both fixed and retested.

- Week 3 plan: feature freeze, automated and non-functional tests, recommendation validation, acceptance scenario, manual, technical documentation, presentation. Final Review on Friday November 20.

# 4. Team Update

Each member answered: what did I finish last week, what will I do this week, and is anything blocking me?

| Team member | Finished last week | Plan for this week | Blockers / help needed |
| --- | --- | --- | --- |
| Jorge Velez Delgado | US28-T3 functional tests executed; two defects registered and retested. | US28-T4 non-functional tests; US28-T5 final acceptance scenario; SPR-T4 presentation. | None. |
| Vicente Rocha Alfaro | US18-T3 and US18-T4 finished. | US18-T5 comparison with spreadsheet; US28-T2 automated test suite; SPR-T3 technical documentation. | None. |
| Oscar Abraham Talavera Nava | US20-T3 and US20-T4 finished; recommendations every 15 min and on new alerts. | US20-T5 delivery to the producer; US20-T6 scenario validation; SPR-T3. | None. |
| Carlos Ramirez Mendoza | US27-T3 and US27-T4 finished; FR-11 defect fixed. | US27-T5 performance and usability; US27-T6 tests; SPR-T2 user manual. | None. |
| Alexis Enrique Valle Parra | US21-T2 and US21-T3 finished. | US21-T4 readability test; US26-T2 and US26-T3; SPR-T2 user manual. | None. |

# 5. Scrum Board and Burndown Status

| Done | 18 tasks (39 h) |
| --- | --- |
| Remaining | 19 h (ideal line: 19 h) |
| Planned for this week | 11 tasks (19 h) + 4 sprint-level tasks |
| Tasks moved to Done last week | US18-T3, US18-T4, US20-T3, US20-T4, US21-T2, US21-T3, US27-T3, US27-T4, US28-T3 |

# 6. Decisions and Action Items

- Feature freeze from today; only defect fixes allowed.

- Final rehearsal on Thursday November 19 at 4:30 PM.

# 7. Meeting Conclusion

All implementation tasks are done; the team enters the final testing and documentation week.